## Week 323 - 327
Task | Team Member | Development | Testing | Integration | Roadblocks
Camera Functionality | Ryan, Holland, Prateek | DONE | DONE | NOT STARTED
Workout State Machine | Ryan | DONE | DONE | NOT STARTED
Data Set Files | Sam | IN PROGRESS | NOT STARTED | NA
Software Training Files | Sam | DONE | IN PROGRESS | NOT STARTED | Waiting on Data Set Files
MAC | Madi | DONE | DONE | NOT STARTED
Bram Ctrl (For weights) | Madi | DONE | DONE | NOT STARTED
MLP Classifier | Madi | IN PROGRESS | IN PROGRESS | NOT STARTED
DPU | Holland | IN PROGRESS | NOT STARTED | NOT STARTED
Camera Processing | Holland, Ryan | DONE | NOT STARTED | NOT STARTED
AXI Communication | Prateek | NOT STARTED | NOT STARTED | NOT STARTED | Waiting to start integration
Top Level Inference |  |  |  |  | Waiting on every module

## Week 46 - 410
Task | Team Member | Development | Testing | Integration | Roadblocks
Camera Functionality | Ryan, Holland, Prateek | DONE | DONE | NOT STARTED
Workout State Machine | Ryan | DONE | DONE | NOT STARTED
Data Set Files | Sam | DONE | IN PROGRESS | NA
Software Training Files | Sam | DONE | IN PROGRESS | NOT STARTED
MAC (PART OF MLP) | Madi | DONE | DONE | NOT STARTED
Bram Ctrl (For weights) (PART OF MLP) | Madi | DONE | DONE | NOT STARTED
MLP Classifier | Madi | DONE | DONE | NOT STARTED
DPU | Holland, Prateek | IN PROGRESS | NOT STARTED | NOT STARTED
Camera Processing | Holland, Ryan | DONE | NOT STARTED | NOT STARTED
AXI Communication | Prateek | NOT STARTED | NOT STARTED | NOT STARTED | Waiting to start integration
Top Level Inference |  |  |  |  | Waiting on every module